## Sheet1
Month | Work Summary | New Learnings | Problems / Issues Encountered
July | Underwent detailed product training, gaining understanding of the core architecture, deployment pipelines, and key backend technologies such as Kafka, Keycloak, Vault, and Airflow. Focused on learning how different components of the Fireflink product interact and function within the system. | Gained foundational understanding of Fireflink’s architecture and backend components including Kafka, Airflow, Vault, and Keycloak. | No major issues — primarily focused on initial product learning and environment familiarization.
August | Worked on V2 On-Prem setup and participated in knowledge transfer (KT) sessions on V3 On-Prem installation and configuration. Learned how the product runs on Docker, including image management and container orchestration. Contributed to initial lower environment deployments, working with Vault, Helm, and Kafka connectors for secure and automated setup. | Learned Docker container management, Vault integration, Helm usage, and connector configuration for On-Prem environments. | Faced minor configuration issues during On-Prem setup and Docker image alignment across environments.
September | Initiated and completed the setup of a lower cloud environment (performance.fireflink.com) from scratch, including installation and configuration of Airflow, Keycloak, Kafka connectors, Vault, ArgoCD, and Helm charts. Set up Jenkins jobs for automation. Additionally, completed the V3 demo environment setup for demo users. Successfully converted MongoDB from standalone to cluster mode for connector integration. Took KT from Manoj K on connector setup. Resolved MongoDB conflicts between the performance and local environments and migrated Kafka from cluster to standalone mode for lower environments (dev2, test2, test3). | Gained deeper understanding of Helm charts, Kafka setup and migration, Airflow workflows, ArgoCD pipelines, Vault, Connectors, Elasticsearch, and Kibana. | Encountered MongoDB conflicts between performance and local environments, and Kafka connectivity issues; resolved with senior support. Adjusted MongoDB from standalone to cluster for connector setup and migrated Kafka to standalone for lower environments.
October | Focused on automation and observability for On-Prem and Cloud environments. Implemented logging and monitoring using Grafana, Loki, and Prometheus. Worked on Helm-based deployments and configuration automation for lower environments. Continued deployments and validation for lower environments throughout August, September, and October. | Learned automation scripting, monitoring setup with Grafana/Loki/Prometheus, and advanced Helm deployment strategies. | Faced challenges integrating monitoring tools with multiple environments and automating Helm deployments, which were successfully resolved.